## 2024
PROCUREMENT PLAN
COUNTRY |  | NIGERIA
PROCURING ENTITY |  | AFRICA CENTRE OF EXCELLENCE IN FUTURE ENERGIES AND ELECTROCHEMICAL SYSTEMS (ACE-FUELS), FEDERAL UNIVERSITY OF TECHNOLOGY, OWERRI
FINANCIAL YEAR |  | 2024
CATEGORY A: WORKS (CONSTRUCTION/RENOVATION/MAINTENANCE)
S/NO | PROJECT DESCRIPTION | PACKAGE NO | LOT NO | LUMP SUM OR BOQ | PROCUREMENT METHOD | BUDGETARY AMOUNT ($) | ADVERT FOR PRE-QUALIFICATION | BID INVITATION DATE | BID CLOSING DATE | BID EVALUATION | SUBMISSION OF BID EVALUATION REPORT | APPROVAL/ | AWARD FEC APPROVAL | CONTRACT AMOUNT | CONTRACT SIGNING | CONTRACT DURATION
[12 empty] | “NO OBJECTION” |  | $
1 | Maintenance of ACE-FUELS Complex | ACEFUELS/WKS/2024/1A | 1 | BOQ | RFQ | 20000 | NA | 2024-01-08 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-24 | NA | NA | 2024-01-27 | 8 Weeks
2 | Maintenance of ACE-FUELS Students Hostel | ACEFUELS/WKS/2024/2A | 2 | BOQ | RFQ | 30000 | NA | 2024-01-08 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-24 | NA | NA | 2024-01-27 | 8 Weeks
3 | Construction of Security Post | ACEFUELS/WKS/2024/3A | 3 | BOQ | RFQ | 15000 | NA | 2024-01-08 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-24 | NA | NA | 2024-01-27 | 8 weeks
4 | Maintenace of ACE-FUELS General Purpose Laboratory | ACEFUELS/WKS/2024/4A | 4 | BOQ | RFQ | 4000 | N/A | 2024-01-09 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-25 | NA | NA | 2024-01-28 | 8 weeks
| TOTAL COST |  |  |  |  | 69000
CATEGORY B: GOODS
1 | Procurement and Installation of Teaching Aids and Teaching Materials | ACEFUELS/GDS/2024/1B | 1 | BOQ | RFQ | 10000 | NA | 2024-01-10 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-29 | NA | NA | 2024-02-05 | 4 Weeks
2 | Procurement of Computer Laboratory Equipments and Workstation | ACEFUELS/GDS/2024/2B | 2 | BOQ | NCB | 40000 | NA | 2024-01-10 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-29 | NA | NA | 2024-02-05 | 4 Weeks
3 | Procurement and Installation of 30KVA Diesel Powered Generator | ACEFUELS/GDS/2024/3B | 3 | BOQ | NCB | 15000 | NA | 2024-01-10 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-29 | NA | NA | 2024-02-05 | 4 Weeks
4 | Procurement and Installation of 50KVA Solar Powered Units within ACEFUELS Complex and Students Hostel | ACEFUELS/GDS/2024/4B | 4 | BOQ | RFQ | 40000 | NA | 2024-01-10 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-29 | NA | NA |  | 4 Weeks
5 | Procurement of Office Equipments (Airconditioners) | ACEFUELS/GDS/2024/5B | 5 | BOQ | RFQ | 4200 | NA | 2024-01-10 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-29 | NA | NA | 2024-01-24 | 4 Weeks
6 | Procurement and Installation of Office Equipments (Laptops, Desktops, Photocopier and Printers) | ACEFUELS/GDS/2024/6B | 6 | BOQ | NCB | 64000 | NA | 2024-01-10 | 2024-02-07 | 2024-02-08 | 2024-02-12 | 2024-02-19 | NA | NA | 2024-02-20 | 4 Weeks
7 | Procurement of Assorted Books and Journals | ACEFUELS/GDS/2024/7B | 7 | BOQ | NCB | 140000 | NA | 2024-01-08 | 2024-01-30 | 2024-01-30 | 2024-01-31 | 2024-01-31 | NA | NA | 2024-01-31 | 4 Weeks
8 | Procurement of Mowing Machine | ACEFUELS/GDS/2024/8B | 8 | BOQ | RFQ | 5000 | NA | 2024-01-09 | 2024-01-23 | 2024-01-24 | 2024-01-26 | 2024-01-29 | NA | NA | 2024-02-02 | 2 weeks
9 | Procurement of General Laboratory Equipments, Consumables and Supplies | ACEFUELS/GDS/2024/9B | 9 | BOQ | NCB | 20000 | NA | 2024-01-08 | 2024-01-30 | 2024-01-30 | 2024-01-31 | 2024-01-31 | NA | NA | 2024-02-02 | 4 Weeks
10 | Procurement and Installation of Solar Energy Laboratory Equipments | ACEFUELS/GDS/2024/10B | 10 | BOQ | NCB | 80000 | NA | 2024-01-08 | 2024-01-30 | 2024-01-30 | 2024-01-31 | 2024-01-31 | NA | NA | 2024-02-02 | 8 Weeks
11 | Procurement and Installation of Softwares and Workstation for Computational Modeling and Simulation Laboratory | ACEFUELS/GDS/2024/11B | 11 | BOQ | NCB | 20000 | NA | 2024-01-08 | 2024-01-30 | 2024-01-30 | 2024-01-31 | 2024-01-31 | NA | NA | 2024-02-02 | 8 Weeks
12 | Procurement and Installation of Equipments/Facilities for ACEFUELS Turnkey Electrochemistry Laboratory | ACEFUELS/GDS/2024/12B | 12 | BOQ | ICB | 1100000 | 2024-01-08 | 2024-01-16 | 2024-01-30 | 2024-01-30 | 2024-01-31 | 2024-01-31 | NA | NA | 2024-02-02 | 24 weeks
13 | Procurement and Installation of 100Nr Students Chairs | ACEFUELS/GDS/2024/13B | 13 | BOQ | NCB | 10000 | N/A | 2024-01-08 | 2024-01-30 | 2024-01-30 | 2024-01-31 | 2024-01-31 | N/A | N/A | 2024-02-02 | 6 Weeks
14 | Procurement and Installation of Furnitures and fittings | ACEFUELS/GDS/2024/14B | 14 | BOQ | NCB | 30000 | N/A | 2024-01-09 | 2024-01-31 | 2024-01-31
| TOTAL COST |  |  |  |  | 1578200
CATEGORY C: SERVICES
1 | Insurance of ACE-FUELS Complex and Laboratory Equipment | ACEFUELS/SCS/2024/1C | 1 | BOQ | RFP | 30000 | NA | 2024-01-10 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-29 | NA | NA | 2024-02-05 | 8 Weeks
| TOTAL COST |  |  |  |  | 30000