## Sheet1
Name of Center | AFRICA CENTRE OF EXCELLENCE IN FUTURE ENERGIES AND ELECTROCHEMICAL SYSTEMS
Institution | FEDERAL UNIVERSITY OF TECHNOLOGY OWERRI |  |  |  | On Schedule
Country | NIGERIA
Center Leader | PROFESSOR EMEKA E. OGUZIE |  |  |  | Behind Schedule
Annual Workplan (Month XXX-Month XXX, Year) | JANUARY 2025-JUNE 2025
Work Plan Activities | Description | Component | Partner Contribution (if relevant) | 2025 Y5Q1 |  |  | 2025 Y5Q2 |  |  | 2025 Y5Q3 |  |  | 2025 Y5Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  |  | Jan | Feb | Jan-Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: Action plan to recruit qualified stydents and faculty\ DLI 3: Quantity of Students
Sub-Action 1a: Action plan to attract regional students and faculty
Activity 1: Develop strategies to attract talented regional postgraduate students: Advertisement material that targets qualified female and regional students | Advertisement material that targets qualified students both male and female, and especially female/ regional students. | Operating Cost | [13 empty] | Timely and targeted advertisement of short course programmes. |  | 10000 | 0 | 0 | ACE-FUELS Centre Leader/International Students Affairs Officer, Communication officer/Training and Education Coordinator
|  | OPERATING COST | [13 empty] | Timely and targeted advertisement of MSc and PhD programmes. |  | 10000 | 0 | 0 | ACE-FUELS Centre Leader/International Students Affairs Officer, Communication officer/Training and Education Coordinator
Activity 2: Regional Outreach, Engagement and Education | Hold national and regional public engagement sessions and student fairs (Targeting women and regional students). Participation in regional workshops. | Operating Cost | [13 empty] | Regional Outreach. Participation in Regional workshops. Number of national and regional students enrolled. |  | 10000 | 0 |  | ACE-FUELS Centre Leader, International Students Affairs Officer, Communication officer, Training and Education Coordinator
Sub-Action 1b: Action plan to facilitate broad regional student attendance and full participation.
Activity 1: Maintenance of ACE-FUELS International Office | Maintenance and running of International Office to provide support for regional students | Operating Cost | [13 empty] | Functional ACE-FUELS International Office, in line with DLI 7 |  | 5000 | 0 | 0 | ACE-FUELS Centre Leader/International Students Affairs Officer
[18 empty] | 10000 | 0 | 0
Activity 2: Provide English language support | Run English Language Support Programme (ELSP) for regional students who do not speak English as first language (10 Students) | Operating Cost | [13 empty] | English language support programme running. Students enrolled for the programme |  | 10000 | 0 |  | ACE-FUELS Centre Leader, International Students Affairs Officer, Coordinator, ELSP
Activity 3 :Provide French Language support for Faculty | Run French Language Support Programme (FLSP) for Faculty and staff to ensure effective communication to Regional students (7 Staff) | Operating Cost | [13 empty] | French language support programme running. Faculty and centre staff enrolled for the programme |  | 10000 |  |  | ACE-FUELS Centre Leader, Coordinator, ELSP
Sub-Action 1c: Action plan to facilitate full student integration with university and host communities
Activity 1: Organize student orientation activities | Set up orientation committee. Organize orientation programmes for the new admitted students and excursion for the Students and ACE-FUELS Management Team | Operating Cost | [13 empty] | Minutes of orientation committee meetings.Approved document(s) for the orientation programme and excursion. Feedback from students. |  | 10000 | 0 | 0 | ACE-FUELS Management Team
Activity 2: Organize annual retreat | Organize annual retreat for all participating staff and students. | Operating Cost | [13 empty] | Approved documents and receipts for annual retreat. Feedback from students |  | 15000 | 0 | 2000 | ACE-FUELS Management Team
Activity 3:Organize sport/cultural activities . | Organize sport/cultural activities for ACE-FUELS students, staff and host communities | Operating Cost | [13 empty] | Album of pictures taken during the event |  | 10000
Action 2:Action plan to achieve training/learning excellence\DLI 4: Quality of Education/Research
Sub-Action 2a: Create efficient and effective learning environments
Activity 1: Optimize learning Environment | 1.Upgrade and maintenance of customized ACE-FUELS FUTO learning management System (LMS) and Online Result Management System (ORMS). 2.Ensure broadband internet access within and around ACE-FUELS facilities. 3.Subscribe to Zoom videoconferencing platform. 4.Deploy ICT services for innovation and participation in NgREN (as per DLI 7.6). 5. Subscribe electronic library systems | Operating Cost 1. 5,000 2. 25,000 3. 2,500 4. 100,000 5. 50,000 | [13 empty] | Availability of modern teaching aids and materials; Availability of computer and simulation/modelling labs; Availability of constant/consistent unlimited internet access. Evidence that students and faculty are receiving improved access to the services (as formulated by each institution). Install facilities for efficient diesel-powered generators and solar power generation. Access to books, journals, e-books, e-journal subscriptions, bibliometric databases. Electronic library system. Access to international journal databases. |  | 182500 | 0 |  | ACE-FUELS Management Team/Physical Planning and Development Unit, FUTO
Activiy 2: | (i)Procure teaching aids, teaching materials, (ii)Maintenance of Solar Power for student hostel and the Centre (iii) 5 Nos. 1.5Hp Air conditioners. (iv) Install 30 kVA solar power system for ACE-FUELS Labs (v) Acquire books, journals, e-books, e-journal subscriptions, bibliometric databases. Upgrade an electronic library system for researchers and establish full access to international journal databases. (I ) Provide adequate security to protect all ACE-FUELS facilities, with armed security, security dogs,safety gadgets and communication facilities, . (II) Provision of non-pharmacological interventions for regular cleaning and disinfecting/fumigating the environment,first aid kits, infrared temperature monitors, hand sanitizers, face masks, air quality monitoring devicesetc within all ACE-FUELS facilities. (III) Cleaning and maintenance of ACE-FUELS facilities(Wages for Cleaners, Groundsman, disinfectant and mowing machine ). | GOODS (i). 10,000 ( ii). 20,000 (iii) 4,200 (iv) 50,000 (v). 90,000 OPERATING COST I. 30,000 II.. 15,000 III. 30,000 | [15 empty] | 249200
Activity 3: Accreditation steps | Undertake International Quality Review for ACE-IMPACT Leading to QAA accreditation of the Institution. | OPERATING COST 1. 100,000 | [13 empty] | International Quality Review Report (IQRR) for International Instutitional accreditation |  | 100000 | 0 |  | ACE-FUELS Management Team/University Librarian/University Director of Academic Planning
Sub-Action 2b: Optimize centre management and administration
Activity 1: Setup administrative offices and student offices | Procure and install office equipment 1.10 Nos Desktops/20 No. Laptops 2. 5 Nos Ordinary Printers 3. 2 No. photocopier 4.Procurement of Furnitures and Fittings 5. 10 kVA solar power system | GOODS 1.40,000 2.20,000 3. 4,000 4. 25,000 5. 10,000 | [13 empty] | Office equipment requirements assessed and identified. Call for tender following Nigerian procurement act guidelines. Tenders received and bidding process completed. Contracts awarded. Office equipment supplied and installed |  | 99000 | 0 |  | ACE-FUELS Management Team
Activity 2: Ensure efficient Centre Administration | 1. Hold project implementation meetings and academic board meetings to facilitate achievment of set objectives of the project timely. 2. Improve timeliness/quality of financial management (External Auditors Fees). 3. Attendance to international/regional workshop and conferences including ACE and AAU activities for Centre Leader, management team and faculty 4.National workshops, conferences, seminars and capacity building activities for management team members, staff and faculty, 5. Transport & Travelling (T&T). 6. Data/ Phone Calls for ACE-FUELS Management Team 7. Wages for Laboratory Technician, Consultant and NYSC Corp members | OPERATING COST 1. 50,000 2. 15,000 3. 150,000 4. 70,000 5. 20,000 6. 10,000 7. 7,000 | [13 empty] | Effective and efficient office administration and management. Enhanced productivity of Centre administration, Management Team and Students. Prompt achievement of implementation milestones. Timely fiduciary reporting. Functional institutional oversight of fiduciary management. Functioning internal audit unit and functioning audit committee. Transparency of ACE expenses, notably the approved budget, annual work plan. IFRs with an annex on detailed expenditures, project financial and procurement audit reports are visibly accessible on the ACE Impact Center’s websites. Efficient Procurement planning. Minutes of statutory project implementation meetings. Number of Staff attending workshops/Conferences and trainings. DLI 6 |  | 322,000.00 |  |  | ACE-FUELS Management Team
Activity 3: General Maintenance | 1.Maintenance of ACE-FUELS Complex/Hostels 2.Maintenance of office Equipment 3.Maintenace of vehicles 4.Maintenance of Power Generating sets and Solar units . 5. Fueling of vehicles 6. Fueling/Diesel for power generating sets 7.Maintenance/upgrade of websites. 8. Vehicle insurance 9. Insurance of ACE-FUELS Complex and Laboratory Equipment | WORKS 1. 50,000 2. 4,000 3.12,500 4.7,000 5.15,000 6. 20,000 7.5,000 8.10,000 9. 30,000 | [15 empty] | 143500
Sub-Action 2c: Optimize student enrollment and commencement in ACE-FUELS programmes
Activity 1: Student screening and recruitment | 1.Screening, shortlisting and communication of successful national and regional students for admission and scholarships into ACE-FUELS MSc and PhD programmes. 2. Recruitment of national/regional students for ACE-FUELS short courses. Registration and on-boarding of successful students. | OPERATING COST 5000 | [13 empty] | Selection criteria documents and dcumented screening guidelines. Issued student admission and scholarship award letters. Student registration documents. Records of externally generated revenue from acceptance fees and other student fees ($659/per students). |  | 5000 | 5000 | 0 | ACE-FUELS Management Team/University Management
Activity 2: Running of ACE-FUELS programmes | Enroll students and run MSC and PhD approved programmes: MSc and PhD in Corrosion Technology; MSc and PhD in Electrochemical Technology; MSc and PhD in Future Energies; MSc and PhD in Nanotechnology, as per ACE-FUELS approved curriculum guidelines. Enroll students and run short professional courses and skills support. Expected number of students: MSc - 35; PhD - 30; Short course - 1000 | 200000 | [13 empty] | Running of MSc/PhD and short professional courses. Lecture materials. Programme timetables. |  | 200000 | 120000 |  | ACE-FUELS Management Team/ACE-FUELS Faculty/FUTO Bursary Unit
Action 3: ACE action plan to achieve teaching and applied research excellence\DLI 4 Action: Quality of Education/Research
Sub-Action 3a: Laboratory upgrade
Activity 1: Maintain ACE-FUELS laboratories | Maintenance of laboratory furniture and fittings for ACE-FUELS general purpose laboratory | WORKS 4,000 | [13 empty] | Laboratory set up and functional. Laboratory commissioned and operational |  | 4000 |  |  | ACE-FUELS Management Team/Physical Planning and Development Unit, FUTO
Activity 2: Install research facilities/equipment | 1.Procure and install relevant general use research equipment 2.Procure consumables and lab supplies. 3. Procure and install software and workstations for computational modeling and simulation, upgrade existing software. 4. Procure and install equipment for Biogas Energy Research Laboratory 5. Procure and install equipment for Geothermal Energy Research | GOODS 1.100,000 2. 20,000 3. 50,000 4. 20,000 5. 20,000 | [13 empty] | Functional laboratories with current research equipment, stocked with chemicals and reagents and various lab supplies. Up to date softwares. Provide commercial lab services |  | 210000 | 10000 | 0
P
Activity 1: Develop core research team | (i) Develop core technical team with enhanced ability and competence to initiate, lead and successfully complete high level research projects in the Centre’s focus areas. Respond to national, regional and international calls for research proposals. (ii)Training and Capacity building for for solar cells and batteries R&D in partner institutions abroad (reserach fellowships, internships) | OPERATING COST (i) 10,000 (ii) 250,000 | [13 empty] | Researchers and students undertake advanced research in research projects in the Centre’s focus areas. Research output disseminated in the form of publications, patents, conference papers, training programmes and workshops. 25 publications envisaged ( national co-authored = 15/Regional/international co-authored = 10). Evidence of external research grants income (DLI 5) |  | 260000 | 15000 | 0 | Center-leader, Research Coordinator
Activity 2: Develop technical capacity | (i) Training technologists, technicians, safety officers. Technologists/technicians with enhanced ability and competence to operate and maintain existing and new research equipment and facilities to support high level research projects in the Centre’s focus areas. | OPERATING COST 7,000 | [13 empty] | Technologists/technicians can effectively man and operate available equipment Laboratories are operated in an efficient and safe manner, with minimal accidents |  | 7000 | 0 | 0
3
Activity 1: Setup ACE-FUELS turnkey Electrochemistry laboratory | Maintenance of ACE-FUELS turnkey Electrochemistry laboratory Equipment | OPERATING COST 10,000 | [13 empty] | Layout plan received and approved |  | 10000 | 0 | 0 | ACE-FUELS Management Team/Bio-Logic Science Instruments
Activity 2: Contract award | (i) Procure, Install and commision Equipments/Facilities for ACEFUELS Turnkey Electrochemistry Laboratory (ii)Procurement and Installation of Softwares for ACEFUELS Turnkey Electrochemistry Laboratory (iii)Procurement of Laboratory Consumables for ACEFUELS Turnkey Electrochemistry Laboratory (iv)Procurement and Installation of Laboratory Furnitures for ACEFUELS Turnkey Electrochemistry Laboratory (v) Procure and install equipment for Solar cells and batteries R&D and modelling (vi) Procure software for solar cells and batteries R&D and modelling (vii) Procurement of chemicals and consumables for Solar cells | GOODS (i)600,000 (ii)300,000 (iii)150,000 (iv)50,000 (v)300,000 (vi)300,000 (vii) 200,000 | [13 empty] | Equipment installed, commissioned and in use |  | 1900000 | 0 | 0 | ACE-FUELS Management Team/Partners
Action 4: ACE action plan to generate revenue from education and research activities\DLI 5 Action: Relevance of Education & Research
Sub-Action 4a: Building capacity for effective research translation
Activity 1: Promoting entrepreneurship | On-site/online workshops and training sessions on intellectual property, entrepreneurship and commercialization strategy. Organize University innovation week and innovation prizes. Establish innovator support funding schemes | OPERATING COST 20,000 | [13 empty] | Workshops and training sessions scheduled and completed. Documentation and participants registration documented |  | 270000 | 0 |  | ACE-FUELS Management Team/Centre for Entrepreneurship Studies (CES), FUTO
Activity 2: Stakeholder engagement | (i) Initiate processes to promote technology transfer by forming linkages between ACE-FUELS investigators and stakeholders and collaborating with industry to jointly pursue start-up demonstrations and implementation. (ii) Community engagement and outreach/sensitization programmes. (iii)Undertake fund raising activities with partners | OPERATING COST (i)10,000 (ii) 20,000 | [13 empty] | Identified interested sectoral partners. Meetings and interactions with sectoral partners. Documented meeting records. Evidence of externally generated revenue from fund raising, |  | 30000 |  | 10000 | ACE-FUELS Management Team/Intellectual Property and Technology Transfer Office (IPTTO) FUTO, ACE-FUELS students/InREST
Sub-Action 4b: Stakeholder engagement
Activity 1: Exchange programmes | Institutionalize faculty and student exchange programmes with sectoral partners to create student internship positions and faculty adjunctship positions | OPERATING COST 15,000 | [13 empty] | Students/faculty placed on internships/adjunctships with sectoral partners. List of students/faculty that have participated in at least 1-month period internships/outreach in relevant sector-relevant institutions (up to 50 participants). Internship/adjunctship reports |  | 15000 |  |  | ACE-FUELS Management Team/Sectoral Partners/WACEENET
Activity 2: Networking | Initiate partnerships with national, regional and international institutions and knowledge networks to evolve novel technologies and approaches, which optimally engage local and regional scientific talents, while linking global expertise. Joint research grants applications. Participation in the PASET Regional Benchmarking initiative. WACEENET network activities | OPERATING COST 40,000 | [13 empty] | Records of affiliation with networks. Participation in network activities. Evidence of joint research grants application. Records of externally generated revenue from research grants income (up to $50,000.00). Documented data on the required indicators for PASET Regional Benchmarking, with an intervention plan to improve performance |  | 40000 | 10000 | 20000 | Centre Leader/National and regional Academic/Sectoral Partners
Sub-Action 4c: Business development
Activity 1: Company Registration | Activity 1: Annual renewal of registration of outfit with Corporate Affairs Commission | OPERATING COST 10,000 | [13 empty] | Evidence of payment of Annual renewal fee . Select management board and shareholders. Registration certificate. Evidence of externally generated revenue from research consultancies. |  | 10000 |  | 0 | Centre Leader/Sectoral Liaison Officer/Legal Sevices Unit, FUTO.
Activity 2: Develop business plan | (i)Initiate research translation and commercialization activities. Develop start-up business plans to promote translation of research breakthroughs and technological innovations into industrial and commercial products and processes (ii)Registration and setup of two(2) new professional associations | OPERATING COST (i) 20,000 (ii)40,000 | [13 empty] | Documented business plans. |  | 70000 | 10000 |  | ACE-FUELS Management Team.
Action 5: Communication
Activity 1: Promote science communication and interaction with the public | Support FUTO Science Communication Team (SciComm FUTO) to communicate activities and output of the Centre and entire university to the public, through newsletters, radio and tv shows. Train members of SciComm FUTO on science communication basics. Organize dissemination workshops. | OPERATING COST 15,000 | [13 empty] | Published SciComm FUTO newsletter. |  | 15000
Activity 2: Branding and digital marketing | Engage digital marketing partners. Develop branding and digital marketing strategy, targetting researchers, students, public and private sector practitioners, government agencies and the general public, through in-person, online and social media platforms. | OPERATING COST 15,000 | [13 empty] | Increased online visibility and public perception of the Centre. Improved interaction and communication to the Centre. Improved stakeholder participation in Centre activities. |  | 15000
[18 empty] | 3997200 | 170000 | 32000