## Procurement Plan Works
COUNTRY: NIGERIA
PROJECT: African Centre of Excellence in Future Energies and Electrochemical Systems (ACEFUELS), PROCUREMENT PLAN FOR JANUARY - DECEMBER 2025 (12 MONTHS)
Loan No
NAME OF INSTITUTION: FEDERAL UNIVERSITY OF TECHNOLOGY, OWERRI (FUTO)
WORKS | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
S/NO. | Description | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
WORKS
1. | Maintenance of ACE-FUELS Building Complex | ACEFUELS/WKS/25/001 | 01 | 20000 | NCB |  |  |  |  | N/A |  | 22-1-25 | 5-3-25 | 14-3-25 | N/A | Plan |  | 21-3-25 |  | 28-3-25
2. | Maintenance of ACEFUELS Students Hostels | ACEFUELS/WKS/25/002 | 02 | 30000 | NCB | [6 empty] | 22-1-25 | 5-3-25 | 14-3-25 | N/A | Plan |  | 21-3-25 |  | 28-3-25
3. | Construction of Security Post | ACEFUELS/WKS/003 | 03 | 15000 | RFQ | [6 empty] | 27-1-25 | 10-2-25 | 17-2-25 |  | Plan |  | 24-2-25 |  | 28-2-25
4. | Maintenance of ACEFUELS General Purpose Laboratory | ACEFUELS/WKS/004 | 04 | 4000 | RFQ | [6 empty] | 27-1-25 | 10-2-25 | 17-2-25 |  | Plan |  | 24-2-25 |  | 28-2-25
5. | Electrification of ACE-FUELS Complex | ACEFUELS/WKS/005 | 05 | 18600 | RFQ | [6 empty] | 27-1-25 | 10-2-25 | 17-2-25 |  | Plan |  | 24-2-25 |  | 28-2-25
| SUBTOTAL | BOQ |  | 87600
| Total Cost |  |  | $87,600.00 | [12 empty] | #REF!
Naira Equivalent

## Procurement Plan Goods
COUNTRY: NIGERIA
PROJECT: African Centre of Excellence in Future Energies and Electrochemical Systems (ACEFUELS), PROCUREMENT PLAN FOR JANUARY - DECEMBER 2025 (12 MONTHS)
Loan No : FGN/WB (LOAN 2022)
NAME OF INSTITUTION: FEDERAL UNIVERSITY OF TECHNOLOGY, OWERRI (FUTO)
GOODS | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
S/NO. | Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
1 | Procurement and Installation of Teaching Aids and Materials | ACEFUELS/GDS/25/01 | 01 | 10000 | RFQ | [6 empty] | 27-1-25 | 10-2-25 | 17-2-25 | N/A | Plan |  | 24-2-25 |  | 28-2-25
2 | Procurement and Installation of Battery and Solar Energy Research Equipment | ACEFUELS/GDS/25/02 | 02 | 100000 | NCB | [6 empty] | 22/1/25 | 5/3/25 | 14/3/25 |  | Plan |  | 21/3/25 |  | 28/3/25
3 | Procurement of General use Research Equipment for the Laboratory | ACEFUELS/GDS/25/03 | 03 | 100000 | NCB | [6 empty] | 22/1/25 | 5/3/25 | 14/3/25 |  | Plan |  | 21/3/25 |  | 28/3/25
4 | Procurement/Installation/Maintenance of Solar Powered Units within ACE-FUELS Complex and Students Hostel | ACEFUELS/GDS/25/04 | 04 | 20000 | NCB | [6 empty] | 22/1/25 | 5/3/25 | 14/3/25 |  | Plan |  | 21/3/25 |  | 28/3/25
5 | Procure and Install 30KVA Solar Energy to ACE-FUELS Labs | ACEFUELS/GDS/25/05 | 05 | 50000 | NCB | [6 empty] | 22/1/25 | 5/3/25 | 14/3/25 |  |  |  | 21/3/25 |  | 28/3/25
6 | Procurement of Office Equipments (Air Conditioners) | ACEFUELS/GDS/25/06 | 06 | 4200 | RFQ | [6 empty] | 27/1/25 | 10-2-25 | 17-2-25 |  | Plan |  | 24-2-25 |  | 28-2-25
7 | Procurement and Installation of Office Equipments (Laptops, Desktops, Photocopiers and Printers) | ACEFUELS/GDS/25/07 | 07 | 64000 | NCB | [6 empty] | 22/1/25 | 5/3/25 | 14/3/25 |  | Plan |  | 21/3/25 |  | 28/3/25
8 | Procurement of Assorted Books and Journals | ACEFUELS/GDS/25/08 | 08 | 90000 | NCB | [6 empty] | 22/1/25 | 5/3/25 | 14/3/25 |  | Plan |  | 21/3/25 |  | 28/3/25
9 | Procurement and Installation of Biogas Energy Research Equipment | ACEFUELS/GDS/25/09 | 09 | 20000 | NCB | [6 empty] | 22/1/25 | 5/3/25 | 14/3/25 |  | Plan |  | 21/3/25 |  | 28/3/25
10 | Procurement of General Laboratory Equipments Consumables and supplies | ACEFUELS/GDS/25/10 | 101 | 20000 | NCB | [6 empty] | 22/1/25 | 5/3/25 | 14/3/25 |  | Plan |  | 21/3/25 |  | 28/3/25
11 | Procurement and Installation of Geothermal Energy Laboratory Equipments | ACEFUELS/GDS/25/11 | 11 | 20000 | NCB | [6 empty] | 22/1/25 | 5/3/25 | 14/3/25 |  | Plan |  | 21/3/25 |  | 28/3/25
12 | Procurement and Installation of Softwares and Workstation for Computational Modelling and Simulation Laboratory | ACEFUELS/GDS/25/12 | 12 | 50000 | NCB | [6 empty] | 22/1/25 | 5/3/25 | 14/3/25 |  | Plan |  | 21/3/25 |  | 28/3/25
13 | Procurement and Installation of Equipment/Facilities for ACEFUELS Turnkey Electrochemistry Laboratory | ACEFUELS/GDS/25/13 | 13 | 600000 | ICB | [6 empty] | 04/2/25 | 18/3/25 | 25/3/25 |  | Plan |  | 1/4/25 |  | 8/4/25
14 | Procurement and Installation of Laboratory Consumables for ACEFUELS Turnkey Electrochemistry Laboratory | ACEFUELS/GDS/25/14 | 14 | 150000 | ICB | [6 empty] | 04/2/25 | 18/3/25 | 25/3/25 |  | Plan |  | 1/4/25 |  | 8/4/25
15 | Procurement and Installation of Softwares for ACEFUELS Turnkey Electrochemistry Laboratory | ACEFUELS/GDS/25/15 | 15 | 300000 | ICB | [6 empty] | 04/2/25 | 18/3/25 | 25/3/25 |  | Plan |  | 1/4/25 |  | 8/4/25
16 | Procurement and Installation of Laboratory Furnitures for ACEFUELS Turnkey Electrochemistry Laboratory | ACEFUELS/GDS/25/16 | 16 | 50000 | NCB | [6 empty] | 22/1/25 | 5/3/25 | 14/3/25 |  | Plan |  | 21/3/25 |  | 28/3/25
17 | Procurement and Installation of Solar Cells and Batteries R&D Modelling Equipment | ACEFUELS/GDS/25/17 | 17 | 300000 | ICB | [6 empty] | 04/2/25 | 18/3/25 | 25/3/25 |  | Plan |  | 1/4/25 |  | 8/4/25
18 | Procurement of Chemicals and Consumables for Solar Cells. | ACEFUELS/GDS/25/18 | 18 | 200000 | ICB | [6 empty] | 04/2/25 | 18/3/25 | 25/3/25 |  | Plan |  | 1/4/25 |  | 8/4/25
19 | Procurement of Furnitures and fittings | ACEFUELS/GDS/25/19 | 19 | 25000 | NCB | [6 empty] | 22/1/25 | 5/3/25 | 14/3/25 |  | Plan |  | 21/3/25 |  | 28/3/25
20 | Procure and Installation of 10KVA Solar Energy to ACE-FUELS | ACEFUELS/GDS/25/20 | 20 | 10000 | RFQ | [6 empty] | 27/1/25 | 10-2-25 | 17-2-25 |  | Plan |  | 24-2-25 |  | 28-2-25
21 | Procurement and Installation of Softwares for Solar Cells and BatteriesR&D Modelling Equipment | ACEFUELS/GDS/25/21 | 21 | 300000 | ICB | [6 empty] | 04/2/25 | 18/3/25 | 25/3/25 |  | Plan |  | 21/3/25 |  | 8/4/25
| TOTAL |  |  | 2483200

## Procurement Plan Consultancy
COUNTRY: NIGERIA
PROJECT: African Centre of Excellence in Future Energies and Electrochemical Systems (ACEFUELS), PROCUREMENT PLAN FOR JANUARY - DECEMBER 2025 (12 MONTHS)
CREDIT NO:
NAME OF INSTITUTION: FEDERAL UNIVERSITY OF TECHNOLOGY, OWERRI (FUTO)
For Contracts under projects approved before the May 2002 Guidelines
|  |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for EOI (where required)
CONSULTANCY |  |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation
S/No. | Description* | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost US$ '000
| Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
1. | Insurance of ACEFUELS Complex and Laboratory Equipment | RFP | Lump-sum | 30000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
2. | Training Technologists,Technicians and safety officers on the ACEFUELS Turnkey Laboratory | QCBS | Lump sum | 100000 |  | Plan | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Non Consulting Services
[5 empty] | Prior R | Plan |  | NA | NA | NA |  |  | Plan | [7 empty] | Plan | NA | NA |  |  | NA |  | Plan
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[6 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Prior R | Plan |  | NA | NA | NA |  |  | Plan | [7 empty] | Plan | NA | NA |  |  | NA |  | Plan
| TOTAL AMOUNT |  |  | 130000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual